QDARIA IMPLEMENTATION PLAN

48-Month Execution Roadmap

February 2026 - February 2030

# Phase 1: Foundation (Months 1-3, March - May 2026)

## Objective: Legal formation, team onboarding, hardware procurement

| Deliverable | Owner | Deadline | Status |
| --- | --- | --- | --- |
| Employment contracts signed (all 14) | Mo / Sharareh | Week 2 | Pending |
| QDaria Holdings AS registration | Sharareh / Gaspar | Week 3 | Pending |
| Subsidiary registrations (Zipminator AS, Qm9 AS) | Sharareh | Week 4 | Pending |
| Bank accounts and financial infrastructure | Gaspar / Lillian | Week 3 | Pending |
| Rigetti Novera 9Q QPU order placed | Mo / Svein-Erik | Week 2 | Pending |
| Bluefors dilution refrigerator order placed | Mo / Svein-Erik | Week 2 | Pending |
| Office/lab space lease signed (Oslo) | Svein-Erik / Lillian | Week 4 | Pending |
| IP strategy and first patent filings | Sharareh / Mo | Week 6 | Pending |
| Brand identity and website launch | Caroline | Week 8 | Pending |
| Investor reporting framework established | Gaspar | Week 6 | Pending |
| HR systems and payroll operational | Lillian | Week 3 | Pending |
| Team communication tools deployed | Fredrik | Week 1 | Pending |
| CSR framework documented | Lindsay | Week 8 | Pending |
| Data infrastructure architecture plan | Yulia | Week 6 | Pending |
| Sales pipeline CRM setup | Nick / Rajesh | Week 4 | Pending |

Phase 1 Budget: $4.2M (hardware procurement $3.5M + first quarter operations $700K)

Phase 1 Review Meeting: March 15, 2026 (6 weeks from kickoff)

# Phase 2: Infrastructure (Months 4-9, June - November 2026)

## Objective: Hardware installation, first experiments, product alpha

| Deliverable | Owner | Deadline | Status |
| --- | --- | --- | --- |
| Rigetti Novera QPU delivered and installed | Svein-Erik / Mo | Month 5 |  |
| Bluefors DR commissioned and tested | Svein-Erik / Mo | Month 6 |  |
| First quantum experiments executed | Mo / Fredrik | Month 6 |  |
| Zipminator beta launch (post-quantum encryption) | Nick / Fredrik | Month 7 |  |
| QDiana educational platform alpha | Caroline / Lindsay | Month 8 |  |
| Academic paper submissions (2+ papers) | Mo | Month 8 |  |
| Cloud quantum benchmarks completed (IBM/AWS) | Mo / Yulia | Month 5 |  |
| KPI dashboard and analytics live | Yulia | Month 5 |  |
| Partnership pipeline: 10+ qualified leads | Rajesh / Nick | Month 9 |  |
| Team culture and wellbeing review | Nils | Month 6 |  |
| Second patent filings (3+) | Sharareh / Mo | Month 9 |  |
| Monthly investor updates operational | Gaspar | Month 4 |  |

Phase 2 Budget: $1.6M (6 months operations at ~$265K/month)

Key Risk: Hardware delivery delays. Mitigation: Cloud quantum access as interim.

# Phase 3: Product Launch (Months 10-18, December 2026 - August 2027)

## Objective: First revenue, commercial products, subsidiary formation

| Deliverable | Owner | Deadline | Status |
| --- | --- | --- | --- |
| Zipminator commercial launch | Nick | Month 10 |  |
| First paying customers (5+) | Nick / Rajesh | Month 12 |  |
| Qm9 FinTech beta launch | Rajesh / Yulia | Month 14 |  |
| QDiana public launch | Caroline / Lindsay | Month 12 |  |
| Subsidiary formation: Zipminator AS, Qm9 AS | Sharareh / Gaspar | Month 12 |  |
| Revenue target: NOK 2M+ ARR | Nick / Gaspar | Month 18 |  |
| Conference circuit: IQT, QCE, Davos | Mo / Rajesh | Ongoing |  |
| Patent portfolio: 5+ filings | Sharareh / Mo | Month 18 |  |
| Team expansion: 3-5 additional hires | Lillian / Mo | Month 15 |  |
| Fibonacci anyon research milestones | Mo / Fredrik | Month 18 |  |

Phase 3 Budget: $2.4M (9 months at ~$265K/month)

Revenue Milestone: NOK 2M ARR triggers Series A preparation.

# Phase 4: Scale & Series A (Months 19-30, September 2027 - August 2028)

## Objective: Series A close, product scaling, international expansion

| Deliverable | Owner | Deadline | Status |
| --- | --- | --- | --- |
| Series A preparation and roadshow | Mo / Gaspar | Month 20 |  |
| Series A close (target $25-40M) | Mo / Gaspar | Month 24 |  |
| QMikeAI climate modeling launch | Fredrik / Mo | Month 22 |  |
| QNilaya drug discovery partnerships | Rajesh / Mo | Month 24 |  |
| Team expansion to 25+ employees | Lillian / Mo | Month 28 |  |
| Patent portfolio: 10+ filings | Sharareh / Mo | Month 30 |  |
| Revenue target: NOK 8M+ ARR combined | Nick / Gaspar | Month 30 |  |
| European market expansion | Rajesh / Nick | Month 28 |  |
| Academic publication in top-tier journal | Mo | Month 24 |  |

Phase 4 Budget: Primarily funded by Series A. Seed runway depleted by Month 30-32.

# Phase 5: IPO Track (Months 30-48, August 2028 - February 2030)

## Objective: Subsidiary IPOs, global presence, industry leadership

| Deliverable | Owner | Deadline | Status |
| --- | --- | --- | --- |
| Zipminator IPO preparation | Mo / Gaspar | Month 30 |  |
| Zipminator IPO execution | Mo / Gaspar | Month 36 |  |
| Qm9 IPO preparation | Mo / Gaspar | Month 36 |  |
| Qm9 IPO execution | Mo / Gaspar | Month 42 |  |
| QDiana IPO preparation | Mo / Gaspar | Month 42 |  |
| International offices (EU, US, Asia) | Rajesh / Svein-Erik | Month 40 |  |
| Revenue target: NOK 50M+ ARR | All | Month 48 |  |
| QDaria Holdings valuation: $100M+ | Mo / Gaspar | Month 48 |  |
| 100+ employees across group | Lillian / Mo | Month 48 |  |

Phase 5 represents the culmination of the QDaria vision: multiple publicly-traded quantum technology companies, each serving distinct market verticals, all powered by proprietary topological quantum computing research.